## Countdown Project
5/26/09 Wind Study Committee Countdown till Non-Commercial Wind Laws passed
Project | 2009-02-17 | 2009-02-24 | 2009-03-03 | 2009-03-10 | 2009-03-17 | 2009-03-24 | 2009-03-31 | 2009-04-07 | 4/9 Thurs Town Board Present #1 | 2009-04-14 | 4/16 Thurs Plan-ning Board Present | 2009-04-21 | 2009-04-28 | 5/5 Tues Public Hearing | 2009-05-12 | 5/14 Thurs Town Board Present #2 | 2009-05-19 | 2009-05-26 | 2009-06-02 | 2009-06-09 | 6/11 Thurs Town Board Float Ideas | 2009-06-16 | 6/18 Thurs Planning Board #2 | 2009-06-23 | 2009-06-30 | 7/2 Thurs Planning Board #3 (if need) | 2009-07-07 | 7/9 Thurs Town Board Recommendtns due | 2009-07-14 | Town Board Public Hearing on Non-Com'l Wind Laws (date TBD) | 2009-07-21 | 2009-07-28 | 2009-08-04 | 2009-08-11 | 8/13 Town Board Vote on Non-Com'l Wind Laws | 8/13+ File with NY State - 9/3 Morat ends.
Research Non-Commercial Wind Laws, Policies & Procedures for Towns, Agencies and Manufacturers | [8 empty] | yes |  | yes |  |  | yes
Research Health & Environmental Wind Issues | [8 empty] | no | X | yes | will come late |  | yes, but likely late | bar: 2009-03-24
Research Wind Laws & Regulations re: • Historical Districts & Properties: • Conservation Easements; • Comprehensive Plan • Zoning Laws (current & proposed) | [10 empty] | X |  | X | X | X | bar: 2009-03-03
Review & recommend changes to Special Use Permit, & Zoning & Building permits. | [8 empty] | yes | X |  | X | X | yes | bar: 2009-03-03
Develop draft comprehensive recommendations for Non-Com'l Wind Zoning Laws, policies & procedures | [8 empty] | yes | X |  | X | X | yes | bar: 2009-03-03

## Countdown Name
5/22/09 Wind Study Committee Countdown till Non-Commercial Wind Laws passed
Name/Event | 2009-02-17 | 2009-02-24 | 2009-03-03 | 2009-03-10 | 2009-03-17 | 2009-03-24 | 2009-03-31 | 2009-04-07 | 4/9 Thurs Town Board Present #1 | 2009-04-14 | 4/16 Thurs Plan-ning Board Present | 2009-04-21 | 2009-04-28 | 5/5 Tues Public Hearing | 2009-05-12 | 5/14 Thurs Town Board Present #2 | 2009-05-19 | 2009-05-26 | 2009-06-02 | 2009-06-09 | 6/11 Thurs Town Board Float Ideas | 2009-06-16 | 6/18 Thurs Planning Board #2 | 2009-06-23 | 2009-06-30 | 7/2 Thurs Planning Board #3? | 2009-07-07 | 7/9 Thurs Town Board Final Recmndtns due | 2009-07-14 | Town Board Public Hearing of Non-Com'l Wind Laws (date TBD) | 2009-07-21 | 2009-07-28 | 8/13 Town Board Vote on Non-Com'l Wind Laws | 8/13+ File Non-Com'l Wind Laws with NY State | 9/3 Non-Commercial Wind Moratorium Ends
Noel Abbott | [8 empty] | yes |  | yes |  |  | yes
Alan Wilson | [8 empty] | no | X | yes | will come late |  | yes, but likely late | bar: 2009-03-24
Harry Marcinak | [10 empty] | X |  | X | X | X | bar: 2009-03-03
Melissa McGrath | [8 empty] | yes | X |  | X | X | yes | bar: 2009-03-03
Peter Sedlmeir | [8 empty] | yes |  | yes |  |  | X | bar: 2009-02-24; 2009-03-10